## Project Timeline
Project Timeline
Date | 2018-01-10 | 2018-08-10 | 15/10/2018 | 22/10/2018 | 29/10/2018 | 2018-05-11 | 2018-12-11 | 19/11/2018 | 26/11/2018 | 2018-03-12 | 2018-10-12 | 17/12/2018 | 24/12/2018 | 31/12/2018 | 2019-07-01 | 14/1/2019 | 21/1/2019 | 28/1/2019 | 2019-04-02 | 2019-11-02 | 18/2/2019 | 25/2/2018
Week Number | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22
Task | Week 1: Find a supervisor and propose the game project.; Week 2: Complete any additional documents required by the supervisor based around completing the game project.; Week 4: Evaluate and turn over/hand in all design documents; Week 5: Setup the game project; Week 6: Create a system that will randomly generate a map within the game engine.; Week 9: Conduct a test evaluating the map generation and make any changes to fix any bugs.; Week 10: Implement some basic colonist functionality which allows for them to move around the map, using a path finding algorithm.; Week 14: Test the viability of the colonists using the algorithm, perform some stress tests with a large number of colonists. Make any required changes to the colonists.; Week 15: Place resources randomly within the map. which will later be used by the player.; Week 17: Implement a system which allows for the colonists to perform jobs, using the previously placed resources.; Week 19: Test the placement of the resources with different maps and test the collection of them.; Week 20: Using the resources allow for the player to place building blocks within the map and create a building system.
Current Week | bar: Week 1 to Week 11
Date | Week 1: 2019-04-03; Week 2: 2019-11-03; Week 3: 18/3/2019; Week 4: 25/3/2019; Week 5: 2019-01-04
Week Number | Week 1: Week 23; Week 2: Week 24; Week 3: Week 25; Week 4: Week 26; Week 5: Week 27; Week 6: End Of Project Implementation.
Task | Week 1: Test the buildings within the game to ensure they work correctly.; Week 2: Implement random events into the game using a list of possible events each with their own functionality.; Week 5: Test Events and hand in final year project.
Current Week
Key
Task | Week 2: Current Week
Break | Week 2: Week Ended
Testing | bar: Week 1

## Random Events To Implement
List Of Events
Good Events | Neutral Events | Bad Events